## Sheet1
Note: Each grouping of tasks do not necessarily need to be done in any particular order. Note: Previously finished tasks were not drafted into this document. Note: README contains information on CRUD privelages, view this when implementing CRUD tasks Note: This listing is not complete, by any means, see the 3rd milestone |  |  |  | Legend; applies to all documents
Requirement Mapping(s) | Task Number | Progress (C/IP/[blank]) | Task | C | Complete
3.1, 3.2, 3.3, 3.4 | 1 | [blank] | Draft basic degree page for each page | IP | In-Progress
3.1, 3.2 | 2 | [blank] | Modify degree pages for Software/Hardware to add associate functionality | [blank] | Not Started
4.3, 4.4, 4.5.1, 4.5.2, 4.5.3, 4.5.4, 4.5.5, 4.5.6 | 3 | [blank] | Add print quota controls to the Resources page | Milestone | Key Progress Point
| 4 | [blank] | Generate About CSET content, determine if this is analogous to Dept. Blurb | * | Wildcard
6.1 | 5 | [blank] | Create CSET "event" main page view | Strikethrough | Cut; possibly temporarily
6.5 | 6 | [blank] | Create restricted access CSET "event" page
4.1, 4.2, 4.3, 4.4, 4.6.1, 4.7.1, 4.7.2, 4.7.3 | 7 | [blank] | Finish Resources page draft
1.2.1, 1.2.2, 1.2.3, 1.2.7 | 8 | [blank] | Add basic CRUD to Faculty Profile page
1.1.1, 1.1.2, 1.1.3 | 9 | [blank] | Add basic CRUD to Faculty listing page
4.7.4, 4.7.5 | 10 | [blank] | Add basic CRUD to documents list on Resources page
| 11 | [blank] | Add basic CRUD to Dept. Chair Blurb
6.2, 6.3, 6.4, 6.5 | 12 | [blank] | Add basic CRUD to CSET "event" page
1.1.2, 1.1.3, 1.2.4, 1.2.5, 1.2.6, 3.9, 3.10, 3.11 | 13 | [blank] | Add authentication conditionals to each appropriate page
8.1, 8.2, 8.3, 8.4, 8.5, 8.6, 8.7 | 14 | [blank] | Create distinguishing between student and faculty privelages
* | 1st Milestone |  | Milestone: This point should be sufficient for rough draft publishing phase
* | 16 | [blank] | CRITICIAL: Get new photo set! Faculty pictures, pictures of Purvine labs, lobbies and halls; see README
1.1.1, 1.2.7 | 17 | [blank] | Update faculty photo entries and relations in database
1.1.1, 1.1.2, 1.1.3 | 18 | [blank] | Refine faculty tile component
1.1.2, 1.1.3 | 19 | [blank] | Enhance faculty tile wrapping mechanics for page responsiveness
1.2.1, 1.2.2, 1.2.3, 1.2.6, 1.2.7 | 20 | [blank] | Refine faculty profile view
4* | 21 | [blank] | Refine resources view
2.1.1 | 22 | [blank] | Implement basic student project functionality; (new view/partial or extend resource view)
2.1.2, 2.1.2, 2.1.3, 2.1.4 | 23 | [blank] | Add basic CRUD to student project implementation
2.1.6 | 24 | [blank] | Implement basic student project deletion request view and faculty approval functionality
2.1.4, 2.1.5 | 25 | [blank] | Add basic faculty monitoring to student projects implementation
| 26 | [blank] | Add CRUD to contacts page
| 27 | [blank] | Add CRUD to about page
3.5, 3.6, 3.7, 3.8 | 28 | [blank] | Add CRUD to degree descriptions pages
| 29 | [blank] | Refine degree content pages as well as the degree tiles page
2.1.1, 2.1.3 | 30 | [blank] | Refine student project implementation
* | 2nd Milestone |  | Milestone: At this point the project should be in a pseudo-refined state
9.1.1, 9.1.2, 9.1.3 | 31 | [blank] | Redesign the database under the csetweb-dev schema
9.1.1, 9.1.2, 9.1.3 | 32 | [blank] | Test integration of the new database design, ensure all features operate as before
* | 33 | [blank] | Update/Optimize any necessary CRUD accesses to the database
* | 3rd Milestone |  | Milestone: Most of the overhaul should be complete by this point; re-evaluate tasks and requirements
| 34 | [blank]
| 35 | [blank]