## Sheet1
Note: Each grouping of tasks do not necessarily need to be done in any particular order. Note: Previously finished tasks were not drafted into this document. Note: README contains information on CRUD privelages, view this when implementing CRUD tasks |  |  |  | Legend
Requirement Mapping(s) | Task Number | Progress (C/IP/[blank]) | Task | C | Complete
| 1 | [blank] | Draft basic degree page for each page | IP | In-Progress
| 2 | [blank] | Modify degree pages for Software/Hardware to add associate functionality | [blank] | Not Started
| 3 | [blank] | Add print quota controls to the Resources page | Milestone | Key Progress Point
| 4 | [blank] | Generate About CSET content, determine if this is analogous to Dept. Blurb
| 5 | [blank] | Create CSET "event" main page view
| 6 | [blank] | Create restricted access CSET "event" page
| 7 | [blank] | Finish Resources page draft
| 8 | [blank] | Add basic CRUD to Faculty Profile page
| 9 | [blank] | Add basic CRUD to Faculty listing page
| 10 | [blank] | Add basic CRUD to documents list on Resources page
| 11 | [blank] | Add basic CRUD to Dept. Chair Blurb
| 12 | [blank] | Add basic CRUD to CSET "event" page
| 13 | [blank] | Add authentication conditionals to each appropriate page
| 14 | [blank] | Create distinguishing between student and faculty privelages
|  | Milestone | Milestone: This point should be sufficient for rough draft publishing phase
| 16 | [blank] | CRITICIAL: Get new photo set! Faculty pictures, pictures of Purvine labs, lobbies and halls; see README
| 17 | [blank] | Update faculty photo entries and relations
| 18 | [blank] | Refine faculty tile component
| 19 | [blank] | Enhance faculty tile wrapping mechanics for page responsiveness
| 20 | [blank] | Refine faculty profile view
| 21 | [blank] | Refine resources view
| 22 | [blank] | Implement basic student project functionality; (new view/partial or extend resource view)
| 23 | [blank] | Add basic CRUD to student project implementation
| 24 | [blank] | Add basic faculty monitoring to student projects implementation
| 25 | [blank] | Add CRUD to contacts page
| 26 | [blank] | Add CRUD to about page
| 27 | [blank] | Add CRUD to degree descriptions pages
| 28 | [blank] | Refine degree content pages as well as the degree tiles page
| 29 | [blank]
| 30 | [blank]